YOUTH EMPOWERMENT FO DEVELOPMENT MINISTRIES (YEDEM) INTERNATIONAL

SIERRA LEONE – PROJECT 002

PROJECT TITLE:			Agriculture for Sustainable Development

CONTACT PERSON:		Sylvanus S. Murray

Founder & General Overseer

YEDEM

murrays@un.org, yedemint@yahoo.com

LEGAL STATUS:			Registered with: Ministry of Youth, Education & Sport; 						Registrar-general’s office; COORD – SL

PROJECT LOCATION;		Pa Lokko Road, Cole Town Village, Waterloo Rural Area

CONTACT ADDRESS:		Youth Empowerment for Development Ministries (YEDEM)

33,Garrison Street

P.O.Box 1465

Freetown,

Sierra Leone,

West Africa.

PROJECT BENEFICIARIES:	Unemployed; Marginalised & Disadvantaged IDP’s & Street					Youths

PROJECT DURATION:		18 Months

BACKGROUND INFORMATION:

Agriculture for Sustainable Development is a project of Youth Empowerment for Development Ministries (YEDEM) on behalf of 140 unemployed and marginalized young people of affiliate youth groups / organisation.

Pursuant of the Organisation’s aim to cater for the Development of young people. YEDEM seeks to help youths without basic or no education at all acquire vocational and practical skills or engage in productive income generating activities to make them self reliant and responsible. YEDEM in collaboration with some of its affiliate youth groups have initiated this project.

The project targets marginalized and unemployed youths of affiliate groups / organisation that can be gainfully engaged in agricultural related activities vis-à-vis production. The Organisation has acquired a 37 acres of land along the Pa Lokko Road at Cole own Village, Waterloo Rural Area for the said purpose. The land belongs to an affiliate group, which has decided to make it available to YEDEM for the intended project.

A total of 140 youths has been mobilised to be gainfully engaged in the project. These youths are mostly Internally Displaced Persons from the IDP camp at Waterloo, unemployed youths from affiliate groups such as Firestone Community Development and Cultural organisation, Bar ham Road Youths, Waterloo Youth Organisaion and marginalized street youths.

These youths have been divided into four groups of thirty-five persons and shall be engaged in the following agricultural activities:

(A)	FARMING:			(i)	Swampland & upland cultivation

(ii)	Vegetable production – pepper, garden eggs, tomatoes,						 cucumber, okra, watermelon and carrot

- Cassava

- Potatoes

- Ground nut

(B)	LIVESTOCK FARMIN	(i)	Piggery

- Poultry – chicken & ducks

- Animal husbandry – goat and sheep

- Rabbit husbandry

PROJECT DECRIPTION:		Four groups of 35 young people shall be engaged in the					 	aforementioned agricultural activities on the 37 acres piece of 					land available at Pa Lokko Road, Cole Town Village, Waterloo			 		Rural Area.

The groups shall be responsible to carryout the clearing of the					bush onto the harvesting of produce. These activities shall 						commence in stages in consonance with the following schedules:

Stage (I)	-	Clearing & burning of bush		-	February / March

Stage (II)	-	Preparation of soil for planting	-	April / May

Stage (III)	-	Planting				-	May

Stage (IV)	-	Maintenance				-	June – September

Stage (V)	-	Harvest				-	September – December

Stage (VI)	-	Post Harvest activities			-	January

The Livestock farming shall be implemented on the following stages:

Stage (i)	-	Building of shed

Stage (ii)	-	Acquisition of Piglets etc

Stage (iii)	-	Medical

Stage (iv)	-	Reproduction (breeding)

Stage (vi)	-	Slaughtering for sale

NOTE:	All proceeds of the project shall be deposited in a special account after which the total 		shall be divided among participants of the project. This is because the project directly		aims at poverty alleviation among the target beneficiaries.

The project shall be administered by the Project Department of YEDEM. A Project Officer assisted by a corps of experienced field workers heads the department. The Project Officer shall submit monthly reports to the Executive of YEDEM through the secretary. The Executive shall summon the project Officer to make specifications and clarifications.

The Board of Trustees of YEDEM known as the Advisory Committee shall monitor	 	and evaluate the project on a bi-monthly basis and make adequate recommendations 		and suggestions to the executive for onward transfer to the project department.

Also the executive together with representatives of the youth groups from which		 	participants are mobilised shall from time to time meet regularly in consultation with	 	regards policy formulation and implementation.

# THE PROJECT ESTIMATE

(A)	FARMING

(i)	SWAMP LAND RICE CULTIVATION

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Rice Seed			40 bushel	       10,000		     400,000.00

2.	Hoe				10		         3,000		       30,000.00

3.	Shovel				10		         8,000		       80,000.00

510,000.00

(ii)	UP-LAND RICE CULTIVATION

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Rice Seed			40 bushes	       10,000		     400,000.00

2.	Cutlass				35		         5,000		     175,000.00

3.	Hoe				10		         3,000		       30,000.00

4.	Shovel				10		         8,000		       80,000.00

5.	Rake				10		         3,000		       30,000.00

715,000.00

(iii)	VEGETABLE CULTIVATION

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Pepper				100 pkt	         2,000		     200,000.00

2.	Garden eggs			100 pkt	         2,000		     200,000.00

3.	Tomatoes			100 pkt	         2,000		     200,000.00

4.	Cucumber			100 pkt	         2,000		     200,000.00

5.	Okra				100 pkt	         2,000		     200,000.00

6.	Water-Melon 			100 pkt	         2,000		     200,000.00

7.	Carrot				100 pkt	         2,000		     200,000.00

1,400,000.00

(iv)	OTHER VARIABLE CULTIVATION

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Corn				100 cups	         3,500		     350,000.00

2.	Cassava Stump		100 bundles	         3,500		     350,000.00

3.	Potato Vine			100 bundles	         3,000		     300,000.00

4.	Groundnut			    5 bags	       50,000		     250,000.00

1,250,000.00

(v)	EQUPMENTS FOR (III) & (IV)

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Cutlass				   35		         5,000		     175,000.00

2.	Rake				   35		         3,000		     105,000.00

3.	Hoe				   35		         3,000		     105,000.00

4.	Shovel				   35		         8,000		     280,000.00

5.	Wheel Barrow			     5		       55,000		     275,000.00

6.	Basket				   40		         1,500		       60,000.00

7.	Watering Can			  10		     35,000		     350,000.00

8.	Measuring Line		    5 pieces	     10,000		       50,000.00

9.	Hand Trowel			150		       5,000		     750,000.00

10.	Spraying Can (Anti-Fungal)	    5		       5,000		     175,000.00

11.	Chemical for Spray		    5 gallons	     10,000		       50,000.00

2,375,000.00

(B)	LIVESTOCK FARMING

I.	PIGERY

a.	CONSTRUCTION OF STY

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Fence Stick			12 doz		     10,000		     120,000.00

2.	Nail				30 pkt		       1,000		       30,000.00

3.	Zinc				  6 bundles	   200,000		  1,200,000.00

4.	Cement			15 bags	     13,000		     195,000.00

5.	Wire Mesh			15 bundle	     10,000		     150,000.00

1,695,000.00

b.	ACQUIRING PIGLETS

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	English Breed			5 pair		     60,000		     300,000.00

2.	Local Breed			5 pair		     50,000		     250,000.00

3.	Cross Breed			5 pair		     40,000		     200,000.00

750,000.00

(C)	FEEDING & MEDICAL

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Feeding for 1 year		    -		          -			   2,000,000.00

2.	Medication			    -		          -			   1,000,000.00

3,000,000.00

II.	POULTRY

a.	CONSTRUCTION OF POULTRY

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Fence Stick			10 doz		     20,000		     200,000.00

2.	Nail				30 pkt		       1,000		       30,000.00

3.	Wire Mesh			15 bundles	     20,000		     300,000.00

4.	Zinc				  3 bundles	   200,000		     600,000.00

5.	Cement			  5 bags	     13,000		       65,000.00

6.	Board 2” x 2”			  5 pieces	     12,000		       60,000.00

7.	Board 2” x 12”		  5 pieces	     12,000		       60,000.00

1,315,000.00

b.	ACQUIRIN CHICKS & DUCKS

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	English Chicks			10 pair		       5,000	       50,000.00

2.	Local Chicks				10 pair		       5,000	       50,000.00

3.	Ducklings				10 pair		       5,000	       50,000.00

150,000.00

c.	FEEDING & MEDICAL

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Feeding for 1 year		   -		          -			   2,000,000.00

2.	Medication			   -		          -			   1,000,000.00

3,000,000.00

III.	ANIMAL HUSBANDARY (GOAT & SHEEP)

a.	CONSTRUCTION OF SHED

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Fence Stick			10 doz		     20,000		     200,000.00

2.	Nail				30 pkt		       1,000		       30,000.00

3.	Wire Mesh			15 bundles	     20,000		     300,000.00

4.	Zinc				  5 bundles	   200,000		  1,000,000.00

5.	Cement			10 bags	     13,000		     130,000.00

6.	Board 2” x 2”			  5 pieces	     12,000		       60,000.00

7.	Board 2” x 12”		  5 pieces	     12,000		       60,000.00

1,780,000.00

b.	ACQUIRING LAMB & GOAT

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Lamb				  5 pair		     60,000		     300,000.00

2.	Goat				  5 pair		     60,000		     300,000.00

600,000.00

c.	FEEDING & MEDICAL

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Feeding for 1 year		   -			-		  2,000,000.00

2.	Medical			   -			-		  1,000,000.00

3,000,000.00

## D.	RABBIT HUSBANDARY

a.	CONSTRUCTION OF SHED

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Wire Mesh			20 bundles	     10,000		     200,000.00

2.	Board 2” x 12”		  4 pieces	     12,000		       48,000.00

3.	Ply Wood			10 pieces	     10,000		     100,000.00

4.	Nail				20 pkt		       1,000		       20,000.00

368,000.00

b.	ACQUIRING YOUNG RABBITS

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Young Rabbits		5 pair		     50,000		     250,000.00

c.	FEEDING & MEDICAL

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Feeding for 1 year		   -			-		  1,000,000.00

2.	Medical			   -			-		  1,000,000.00

2,000,000.00

## E.	EQUPMENTS / TOOLS

NO.	ITEM REQUIRED		QTY		UNIT COST		TOTAL COST

1.	Long Broom			30		       2,000		       60,000.00

2.	Watering Can			10		     35,000		     350,000.00

3.	34cm Kettle			10		     15,000		     150,000.00

4.	Big Rubber Bowl		10		     20,000		     200,000.00

5.	Wheel Barrow			  5		     55,000		     275,000.00

6.	Spraying Can			  5		     35,000		     175,000.00

7.	Chemical (Disinfectant)	15 gallons	     10,000		     150,000.00

1,360,000.00

F.	PERSONNEL

Project Manager	1	18 months		500,000		  9,000,000.00

Project Coordinator	1	18 months		400,000		  7,200,000.00

Secretary		1	18 months		200,000		  3,600,000.00

Janitor			1	18 months		100,000		  1,800,000.00

Miscellaneous						200,000		  3,600,000.00

25,200,000.00

GRAND TOTAL = LE50,718,000.00 (US $23,054.00)